## Active Projects
Development Timescale
Current
Monthly Dates | [6 empty] | 2019-09-01 |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01
Weekly Dates | time axis 2019-09-16 to 2020-10-12
Projects | Description | % | Status | Time Frames | Reason | Team Members
Markerstudy Updates | MTA Changes & Renewals | 90% | Delayed | 1 Weeks | Trade X | Michael | 2019-11-25: Live; 2020-06-01: Testing; 2020-06-08: Live
Renewals | System Duplication Uploader, Testing | 80% | On Track | 2-3 Weeks |  | Fred, Ed | 2020-06-15: Testing; 2020-06-22: Live
Eridge Underwriting | Test Rate, Docs & Bordraux | 80% | On Track | 1-2 Weeks |  |  | 2020-06-01: Borderaux; 2020-06-08: Testing; 2020-06-15: Live
Credit Check API | XSD & Testing | 70% | On Track | 1-2 Weeks |  |  | 2020-06-08: Live
Reports 1 - Manager Reports |  | 80% | On Track | 1 Weeks |  | Michael, Joe | 2019-11-25: Live; 2020-06-15: Live
Reports 2 - Tracking & Landing Pages |  | 15% | On Track | 5-6 Weeks |  | Joe, Scott, Fred | 2020-07-06: Live
Reports 3 - Reporting Office |  | 10% | Planning | 4-5 Weeks |  | Joe, Scott, Fred
SSP Intergration |  | 0% | Planning | ?? |  | Ed, Michael, Tom, Fred
My Portal & Admin |  | 10% | Planning |  |  | Joe, Scott
GDPR |  | 40% | Planning |  |  | Michael, Scott
Auto Text & Email |  | 40% | Planning |  |  | Ed, Tom
NCI API |  | 20% | Planning |  |  | Ed, Tom
Clearwater API |  | 0% | Not Started |  |  | Tom
Stuben Edge Schemes |  | 0% | Not Started |  |  | Joe, Michael, Ed
Website Review |  | 0% | Not Started
Admin Automatic |  | 10% | Planning
Hosting Review & Switch |  | 10% | Planning
Jason Tweaks - PC system |  | 45% | Planning |  |  | Joe, Scott
Jack Tweaks - MT system |  | 85% | Planning |  |  | Joe, Scott,Ed
Quartix - Self Fit Box - Script and options |  | 0% | Not Started
Vehicle Reg Lookup - CDL & Thatchams |  | 0% | Not Started
Jase - excess protect script onto the £1000 level |  | 0% | Not Started
PC - Legal Protection - API / Borderaux to Kingsway (JAW) |  | 0% | Not Started
Honcho - auto apply Think Discount…. & override "No" black box |  | 0% | Not Started

## Completed Projects
Development Timescale
Current
Monthly Dates |  |  |  |  | 2019-09-01 |  |  | 2019-10-01 |  |  |  | 2019-11-01 |  |  |  | 2019-12-01 |  |  |  |  | 2020-01-01 |  |  |  | 2020-02-01 |  |  |  | 2020-03-01 |  |  |  |  | 2020-04-01 |  |  |  | 2020-05-01 |  |  |  | 2020-06-01 |  |  |  |  | 2020-07-01
Weekly Dates | time axis 2019-09-16 to 2020-07-06
Projects | Status | Time Frames | Reason | Team Members
Online Prices | Live & Resolved |  |  |  | 2019-09-16: Live; 2019-09-23: Resolved
Honcho | Live & Resolved |  |  |  | 2019-09-16: Live; 2019-09-23: Resolved
Quotes & Wessex | Live & Resolved |  |  |  | 2019-12-09: Live; 2019-12-30: Resolved
TradeX | Live & Resolved |  |  |  | 2019-12-16: Live; 2019-12-30: Resolved
Tradewise Vanilla Updates | Removed
Zenith Scrape | Live & Resolved |  |  | Tom | 2019-11-04: Tom; 2020-02-17: Live
Covera Scrape | Live & Resolved |  |  | Tom | 2019-11-04: Tom; 2020-02-17: Live
TFP Scrape | Live & Resolved |  |  | Fred | 2019-11-04: Fred; 2020-02-24: Live

## Daily Tasks
Daily Tasks / Activity:
Team Call
Update JW

## Monthly Tasks
Monthly Tasks / Activity:
Update Invoices / Budget Sheet
Team 1-2-1s